## Francis
SUMMARY OF CAPITAL IMPROVEMENT PROJECTS
Jurisdiction: Francis City
Date: September 2021
SHORT TERM (1 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | EST. START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1 | 1000 East Water Improvements | 300000 | 2022 | Water Impact Fees, CDBG, Drinking Water, Water Resources | Water
2 | Drinking Water Source | 1500000 | 2021 | Water Impact Fees, CIB, Drinking Water, Water Resources | Water
3 | Drinking Water Storage Tank | 1500000 | 2022 | Water Impact Fees, CIB, Drinking Water, Water Resources | Water
4 | Upgrade Hallam Road Lift Station | 200000 | 2021 | Sewer Impact Fees, Sewer Fund | Sewer
5 | Road Improvements | 100000 | 2021 | General Fund, SC Transportation Tax, B&C Roads | Roads
6 | Public Works Building Expansion | 150000 | 2021 | Water Fund, Sewer Fund, General Fund | Water, Sewer, Roads
7 | Wild Willow Bike Park | 325500 | 2022 | RAP Tax, General Fund | Parks
8 | Francis Park Improvements | 675000 | 2022 | RAP Tax, General Fund | Parks
9
10
MEDIUM TERM (5 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | ESTIMATED START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1 | Upgrade Foothill Lift Station | 350000 | 2023 | Sewer fund, Sewer Imact Fees, Developer Funding | Sewer
2 | Community Center Upgrades | 100000 | 2023 | General Fund | Parks, Buildings
3 | Road Improvements and Maintenance | 100000 | Yearly | General Fund, SC Transportation Tax, B&C Roads | Roads
4
5
6
7
8
9
10
LONG TERM (5-10 YEARS)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | ESTIMATED START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1
2
3
4
5
NEEDS AND PRIORITIES
| IDENTIFIED NEED | COST | SOURCE | PRIORITY | START
| Drinking Water Source | 1500000 | Impact Fees, CIB, Drinking Water, Water Resources | 1 | 2020-2021
| Drinking Water Storage Tank | 1500000 | Impact Fees, CIB, Drinking Water, Water Resources | 2 | 2022
| City Building | 2000000 | Water Fund, Sewer Fund, General Fund | 3 | 2023

## Henefer
SUMMARY OF CAPITAL IMPROVEMENT PROJECTS
Jurisdiction: Henefer Town
Date: September 3, 2021
SHORT TERM (1 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | EST. START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1 | Secondary Water System | 3000000 | 2022 | DWRe/BOR/Town Funds | Town Council
2 | Town Hall Renovation/Community Center | 200000 | 2022 | ARPA/Town Funds | Town Council
3 | Culinary Water Well | 2000000 | 2022 | DWQ/CIB/Town Funds | Town Council
4 | Culinary Water Tank 650,000 gallon | 600000 | 2022 | Town Funds/DWQ/CIB | Town Council
5 | Wastewater Facilities Plan | $40,000 -$50,000 | 2022 | CDBG/CIB/DWQ | Town Council
6
7
8
9
MEDIUM TERM (5 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | ESTIMATED START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1 | Chip and Seal Roads | 180000 | 2022 | B&C road Funds | Town Council
2 | Wastewater Lift Station | 100000 | 2022 | DWQ/CDBG | Town Council
3 | Cemetery Expansion | 250000 | 2025 | Town Funds | Town Council
5
6
7
8
9
10
LONG TERM (5-10 YEARS)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | ESTIMATED START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1 | Replacing UV disinfection and retrofit of the building System for the Wastewater | $250000 to $500,000 | 2025 | USDA/DEQ/CIB | Town Council
2
3
4
5
NEEDS AND PRIORITIES
| IDENTIFIED NEED | COST | SOURCE | PRIORITY | START
| Secondary Water System | 3000000 | DWR/BOR/Town Funds | 1 | Spring 2022
| Culinary Water Well | 3000000 | DWQ/CIB/Town Funds | 2 | Summer 2022
| Culinary Water Tank 650,000 | 600000 | DWQ/CIB/Town Funds | 3 | Fall 2021
| Town Hall Community Center | 200000 | ARPA/Town Funds | 4 | Fall 2022
| Chip & Seal Roads | $180,00 | B&C Road Funds | 5 | Fall 2022
| Wastewater Facilities Plan | $40,000 - $50,000 | CDBG/CIB/DWQ | 6 | Spring 2022
| Wastewater Lift Station | 100000 | DWQ/CDBG | 7 | Spring 2025
| Cemetery Expansion | 250000 | Town Funds | 8 | Spring 2025

## Heber
SUMMARY OF CAPITAL IMPROVEMENT PROJECTS
Jurisdiction: Heber City Corporation
Date: September 14, 2021
SHORT TERM (1 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | EST. START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1 | Phase 1 of Downtown Water and Sewer Replacement | 24000000 | 2022 | Local, CIB, CDBG | Engineering
2 | Eastern Bypass Road | 2500000 | 2022 | Local, CIB | Engineering
3 | Traffic Improvement Study | 150000 | 2021 | Local, CIB | Engineering
4 | I-001 Pressurized Irrigation Project - Central Heber | 511000 | 2022 | DP/Other | Engineering
5 | Red Ledges Park Fitness Court and Trails | 2764000 | 2021 | Impact Fees, Local, CIB, DP/Other | Cemetary and Parks
6 | Muirfield Park Expansion and Amenities | 3642000 | 2022 | Local, CIB, Impact Fees | Cemetary and Parks
7 | Main Street Park Amenities | 0 | 2022 | Local, CIB, Impact Fees | Cemetary and Parks
8 | Cemetary Phase 1 Expansion - Consultation Center and Cremation Phase | 2976000 | 2021 | Local, CIB, Impact Fees | Cemetary and Parks
9 | Coyote Park Construction | 1775000 | 2022 | Local, CIB, Impact Fees | Cemetary and Parks
10 | Parkview Place Park | 75000 | 2021 | Local, CDBG | Planning
11 | Wasatch Vista Park | 75000 | 2021 | Local, CDBG, Impact Fees | Planning
12 | D-025 Storm Water Management Program | 35000 | 2022 | Local | Engineering
13 | D-030 North Village Storm Water System | 15000 | 2022 | DP/Other | Engineering
14 | I-004 Daniel Rd - 1450 S to 1300 S (8") | 300000 | 2022 | Impact Fees, DP/Other | Engineering
15 | I-008 East ByPass - 1500 E to 1240 E (16") | 192000 | 2022 | DP/Other | Engineering
16 | I-011 300 E - 800 N to Coyote Ln Canal Pipe (12") | 115000 | 2022 | Impact Fees, DP/Other | Engineering
17 | I-012 East Bypass - Hwy 40 to 300 E (12") | 92000 | 2022 | Impact Fees | Engineering
18 | I-017 Annual Irrigation Main/Sys Replacements | 51000 | 2022 | Local | Engineering
19 | I-018 East ByPass - 800 E to 300 E | 292000 | 2022 | Impact Fees, DP/Other | Engineering
20 | I-019 1000 E - 1200 S to 1600 S (8") | 87000 | 2021 | Impact Fees, DP/Other | Engineering
21 | I-021 1000 East - 1900 S to Hwy 40 (8") | 163000 | 2022 | Impact Fees, DP/Other | Engineering
22 | I-025 Coyote Lane - 300 E (I-11) to East of Canal | 68000 | 2022 | Impact Fees, DP/Other | Engineering
23 | I-028 Citywide PI Meter Replacements | 1390000 | 2022 | Impact Fees, DP/Other | Engineering
24 | P-034 East Bypass Trail - 550 E to Hwy 40 | 146000 | 2022 | Impact Fees, DP/Other | Engineering
25 | P-035 East Bypass Trail - Center St to Mill Rd | 295000 | 2022 | DP/Other | Engineering
26 | P-040 Coyote Lane Trail | 120000 | 2022 | Impact Fees, DP/Other | Engineering
27 | P-048 Red Ledges Community Park | 203000 | 2022 | DP/Other | Engineering
28 | P-052 Park Equipment (various locations) | 49000 | 2022 | Impact Fees | Engineering
29 | P-054 2400 S Trail - Daniel Elem to Mill Rd | 39000 | 2022 | Impact Fees, DP/Other | Engineering
30 | P-060 IHC Trail - 1200 S to Hwy 40 | 163000 | 2022 | Impact Fees, DP/Other | Engineering
31 | P-065 Mill Road Trail - 1700 S to 2400 S | 203000 | 2022 | Local, DP/Other | Engineering
32 | P-067 600 South Trail - 500 E to 600 E | 34000 | 2021 | Local, DP/Other | Engineering
33 | P-073 Wasatch Vista Neighborhood Park (1.5 ac) | 186000 | 2021 | Impact Fees, DP/Other, CDBG | Engineering
34 | P-075 South Bypass Trail - Daniels Rd to Why 40 | 139000 | 2021 | Impact Fees, DP/Other | Engineering
35 | S-024 1500 West - 100 S to 12100 S (12") | 568000 | 2022 | Impact Fees, DP/Other | Engineering
36 | S-030 Annual Sewer Main/Sys Replacements | 150000 | 2022 | Local | Engineering
37 | S-036 700 N - Main St to 550 E (8") | 377000 | 2022 | DP/Other | Engineering
38 | S-042 1450 South - Daneil Rd to Industrial Pkwy (10") | 679000 | 2022 | Impact Fees | Engineering
39 | S-043 1000 East - 1600 S to Hwy 40 (8") | 168000 | 2022 | DP/Other | Engineering
40 | T-021c 600 South - 500 E to 600E * | 47000 | 2022 | Local, Impact Fees | Engineering
41 | T-024 Coyote Lane - Main to Vly Hills Blvd & Bridge | 788000 | 2022 | Impact Fees, DP/Other | Engineering
42 | T-040 1200 East - 1200 S to Hwy 40 * | 1047000 | 2022 | Impact Fees, DP/Other | Engineering
43 | T-041 Southfield Rd - 100 S to 1200 S | 220000 | 2022 | Local, Impact Fees, DP/Other | Engineering
44 | T-051 1000 East - 1200 S to Hwy 40 | 807000 | 2022 | Impact Fees, DP/Other | Engineering
45 | T-053 East Bypass - Center St to 1050 E | 2343000 | 2022 | DP/Other | Engineering
46 | P-054 2400 S Trail - Daniel Elem to Mill Rd | 534000 | 2022 | Impact Fees, DP/Other | Engineering
47 | T-055 South Bypass - Daniel Rd to Hwy 40 UDOT | 2617000 | 2022 | Impact Fees, DP/Other | Engineering
48 | T-057 East Bypass - 1050 E to 550 E | 298000 | 2022 | Impac Fees | Engineering
49 | T-058 East Bypass - Main St to 550 E | 907000 | 2022 | Impact Fees, DP/Other | Engineering
50 | T-060 Annual Rd Maint - Stripe, Seal, Overlay, Dips | 485000 | 2022 | Local | Engineering
51 | T-061 Annual Sidewalk New Construction & Repair | 262000 | 2022 | Local | Engineering
52 | T-063 Intersection Align Hwy 40 and 2400 S UDOT | 221000 | 2022 | Impact Fees, DP/Other | Engineering
53 | T-064 Intersection Align Hwy 40 and Mill Rd UDOT | 253000 | 2022 | Impact Fees, DP/Other | Engineering
54 | T-066 High-T Intersection at Daniel Rd | 338000 | 2022 | Impact Fees | Engineering
55 | T-069 1900 South - Mill Rd to 500 E | 925000 | 2021 | Impact Fees, DP/Other | Engineering
56 | T-077 Bridge - Replace 760 N Mill Rd | 350000 | 2022 | Local | Engineering
57 | T-078 Master Plan North Cillage Streets | 15000 | 2022 | Local | Engineering
58 | W-007 East Bypass - Hwy 40 to Vly Hills Blvd (12") | 667000 | 2022 | Impact Fees, DP/Other | Engineering
59 | W-008 1900 South - Hwy 40 to Mill Rd (12") | 313000 | 2022 | Impact Fees, DP/Other | Engineering
60 | W-023 Coyote Lane PRV | 134000 | 2022 | Impact Fees | Engineering
61 | W-042 1500 South - Daniels Rd to Hwy 40 (8") | 188000 | 2022 | DP/Other | Engineering
62 | W-056 Annual Water Main/Sys Replacements | 1070000 | 2022 | Local | Engineering
63 | W-061 Hwy 40 - Coyote Ln to 850 N (12") | 519000 | 2022 | Impact Fees, DP/Other | Engineering
64 | W-062 1000 East -1200 S to Hwy 40 (10") | 430000 | 2022 | Impact Fees, DP/Other | Engineering
65 | W-070 Valley Hill Tak 2 Repairs | 460000 | 2022 | Local, Impact Fees | Engineering
MEDIUM TERM (5 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | ESTIMATED START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1 | Land Purchase for Affordable Housing | 1000000 | 2022 | Local, CDBG, CIG | Planning
2 | Airport - Northeast Hanger Taxilane (design and construction) | 306000 | 2022 | Federal, State, Local | Airport
3 | D-023 Master Plan Updates every 5 years (4 times). | 11000 | 2023 | Local | Engineering
4 | D-025 Storm Water Management Program | 259000 | 2023 | Local | Engineering
5 | D-029 Main St to 600 S Ditch Replacement | 326000 | 2023 | Local | Engineering
6 | D-015 Annual Ditch/Storm Drain Imp. | 750000 | 2023-2026 | Local | Engineering
7 | I-001 Pressurized Irrigation Project - Central Heber | 2141000 | 2023-2026 | DP/Other | Engineering
8 | I-003 1200 W - 200 S to 650 S | 295000 | 2023 | Impact Fees, DP/Other | Engineering
9 | I-004 Daniel Rd - 1450 S to 1300 S (8") | 108000 | 2023 | Impact Fees, DP/Other | Engineering
10 | I-011 300 E - 800 N to Coyote Ln Canal Pipe (12") | 205000 | 2023 | Impact Fees, DP/Other | Engineering
11 | I-012 East ByPass - Hwy 40 to 300 E (12") | 90000 | 2023 | Impact Fees, DP/Other | Engineering
12 | I-014 Aerial Digital Map Updates (4 times) | 5000 | 2023 | Impact Fees | Engineering
13 | I-015 Master Plan Updates every 5 years (4 times) | 71000 | 2023 | Impact Fees | Engineering
14 | I-017 Annual Irrigation Main/Sys Replacements | 204000 | 2023-2026 | Local | Engineering
15 | I-018 East ByPass - 800 E to 300 E | 286000 | 2023 | Impact Fees, DP/Other | Engineering
16 | I-021 1000 East - 1900 S to Hwy 40 (8") | 80000 | 2022 | Impact Fees, DP/Other | Engineering
17 | I-023 1600 South - 500 E to 1000 E (6") | 127000 | 2023 | DP/Other | Engineering
18 | I-024 500 East - 1300 S to Hwy 40 (6") | 176000 | 2024 | DP/Other | Engineering
19 | I-028 Citywide PI Meter Replacements | 1410000 | 2022-2025 | Local | Engineering
20 | P-036 Center Creek Trail | 208000 | 2023 | Impact Fees, DP/Other | Engineering
21 | P-037 Mill Road Trail - 1200 S to 1700 S | 146000 | 2023 | Impact Fees, DP/Other | Engineering
22 | P-050 1000 North Trail - Mill Rd to 550 E | 138000 | 2023 | Impact Fees, DP/Other | Engineering
23 | P-052 Park Equipment (various locations) | 115000 | 2023 | Impact Fees | Engineering
24 | P-053 1200 South Trail - 600 E to 1200 E * | 147000 | 2025 | Impact Fees, DP/Other | Engineering
25 | P-055 Lower Wasatch Canal Trail and Bridge | 173000 | 2023 | Local, Impact Fees | Engineering
26 | P-064 600 South Trail - Main St to 600 W | 139000 | 2023 | Local, Impact Fees | Engineering
27 | P-070 Coyote Springs Park | 1775000 | 2024 | DP/Other | Engineering
28 | P-074 New Community Park - Loc Unknown (8.5 ac) | 1053000 | 2024 | Impact Fees | Engineering
29 | P-076 Stewart Neighborhood Park (2ac) | 247000 | 2026 | Impact Fees, DP/Other | Engineering
30 | P-078 Master Plan Updates every 5 years (4 times) | 16000 | 2023 | Impact Fees | Engineering
31 | S-004 500 East - 1200 S to 1900 S (15") | 460000 | 2024 | Impact Fees, DP/Other | Engineering
32 | S-020 Aerial Digital Map Updates (4 times) | 5000 | 2023 | Impact Fees | Engineering
33 | S-021 Master Plan Update (4 times) | 59000 | 2023 | Impact Fees | Engineering
34 | S-023 Highway 40 - Center Cr Dr to 2200 S West (8") | 216000 | 2025 | DP/Other | Engineering
35 | S-023 Highway 40 - Center Cr Dr to 2200 S West (8") | 734000 | 2024-20226 | DP/Other | Engineering
36 | S-024 1500 West - 100 S to 1200 S (12") | 556000 | 2022 | Impact Fees, DP/Other | Engineering
37 | S-030 Annual Sewer Main/Sys Replacements | 11600000 | 2023-2026 | Local | Engineering
38 | S-035 Center Street - 800 E to 1300 E (8") | 411000 | 2024 | DP/Other | Engineering
39 | S-044 500 East - 1900 S to Hwy 40 (10") | 64000 | 2024 | Impact Fees, DP/Other | Engineering
40 | S-045 1200 South - 1000 E to 1200 E | 438000 | 2023 | Impact Fees, DP/Other | Engineering
41 | S-046 550 East - Valley Hlls Dr to 600 N (10") | 510000 | 2024 | Impact Fees, DP/Other | Engineering
42 | T-017 1600 South - 500 E to 1200 East | 533000 | 2023 | Impact Fees, DP/Other | Engineering
43 | T-020 650 S - 800 W to S. Field Rd | 127000 | 2023 | Impact Fees | Engineering
44 | T-029 500 East - 1200 S to East Airport Rd | 1154000 | 2024 | Impact Fees, DP/Other | Engineering
45 | T-040 1200 East - 1200 S to Hwy 40 * | 113000 | 2023 | Impact Fees, DP/Other | Engineering
46 | T-041 Southfield Rd - 100 S to 1200 S | 1472000 | 2023-2025 | Local, Impact Fees, DP/Other | Engineering
47 | T-042 Master plan Update (4 times) | 64000 | 2023 | Impact Fees | Engineering
48 | T-045 1200 South - 820 E to 1200 E * | 500000 | 2024 | Impact Fees, DP/Other | Engineering
49 | T-050 2400 South - 700 E to Hwy 40 * | 523000 | 2024 | Impact Fees, DP/Other | Engineering
50 | T-057 East Bypass - 1050 E to 550 E | 2680000 | 2023 | Impac Fees | Engineering
51 | T-060 Annual Rd Maint - Stripe, Seal, Overlay, Dips | 7176000 | 2023-2026 | Local | Engineering
52 | T-061 Annual Sidewalk New Construction & Repair | 816000 | 2023-2026 | Local | Engineering
53 | T-063 Intersection Align Hwy 40 and 2400 S UDOT | 515000 | 2024 | Impact Fees, DP/Other | Engineering
54 | T-064 Intersection Align Hwy 40 and Mill Rd UDOT | 380000 | 2023 | Impact Fees, DP/Other | Engineering
55 | T-069 1900 South - Mill Rd to 500 E | 945000 | 2023 | Impact Fees, DP/Other | Engineering
56 | T-070 Downtown Parking - 400 N to 500 S (partial) | 117000 | 2025 | Impact Fees | Engineering
57 | T-076 Signal - 1200 E 500 E | 230000 | 2024 | Local | Engineering
58 | T-079 1200 W Rail Road Crossing Improvements | 200000 | 2023 | Local | Engineering
59 | W-008 1900 South - Hwy 40 to Mill Rd (12") | 125000 | 2023 | Impact Fees, DP/Other | Engineering
60 | W-028 Master Plan Updates every 5 years (4 times) | 59000 | 2023 | Impact Fees | Engineering
61 | W-029 Aerial Digital Map Updates (4 times) | 5000 | 2023 | Impact Fees | Engineering
62 | W-035 700 North - Main St to 550 E (8") | 270000 | 2023 | DP/Other | Engineering
63 | W-038 500 South - 300 W to Main St (8") * | 229000 | 2023 | Local, Impact Fees | Engineering
64 | W-041 Hwy 40 - 2200 S to 2400 S West (8") * | 157000 | 2023 | Impact Fees | Engineering
65 | W-043 Hwy 40 - 1300 S to 1700 S (8") | 113000 | 2023 | DP/Other | Engineering
66 | W-056 Annual Water Main/Sys Replacements | 9800000 | 2023-2026 | Local | Engineering
67 | W-061 Hwy 40 - Coyote Ln to 850 N (12") | 256000 | 2025 | Impact Fees, DP/Other | Engineering
68 | W-067 500 East - 1200 S to Hwy 40 (8") | 308000 | 2023 | Impact Fees | Engineering
LONG TERM (5-10 YEARS)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | ESTIMATED START DATE | REVENUE SOURCES/ AMOUNTS | RESP DEPT
1 | Airport - Pavement Preservation | 592000 | 2024 | Federal, State, Local | Engineering
2 | D-015 Ditch Storm Drain System Improvements | 91000 | 2027-2040 | Local | Engineering
3 | D-016 First Flush Detention Pond(s) - Central Heber | 737000 | 2027-2040 | Local | Engineering
4 | D-022 Maintain Existing SD/Ditch System (20 times) | 2354000 | 2027-2040 | Local | Engineering
5 | D-023 Master Plan Updates every 5 years (4 times). | 34000 | 2027-2040 | Local | Engineering
6 | D-026 Install SD System in Old Town Heber | 0 | 2027-2040 | Local, Impact Fees | Engineering
7 | D-028 Heber City Public Works Facility Exp Ph 2* | 482000 | 2027-2040 | Impact Fees | Engineering
8 | I-001 Pressurized Irrigation Project - Central Heber | 4714000 | 2027-2040 | DP/Other | Engineering
9 | I-002 1200 W & 850 W - 100 S to 500 N | 321000 | 2027-2040 | Impact Fees, DP/Other | Engineering
10 | I-006 900 North - Source to East By-pass Rd | 0 | 2027-2040 | N/A | Engineering
11 | I-010 Valley Hills Blvd - Mill Rd to Callaway Dr * | 0 | 2027-2040 | N/A | Engineering
12 | I-013 Regulation Pond(s) (27 af) | 2490000 | 2027-2040 | Impact Fees | Engineering
13 | I-014 Aerial Digital Map Updates (4 times) | 16000 | 2027-2040 | Impact Fees | Engineering
14 | I-015 Master Plan Updates every 5 years (4 times) | 212000 | 2027-2040 | Impact Fees | Engineering
15 | I-016 Regulation Pond(s) | 0 | 2027-2040 | N/A | Engineering
16 | I-017 Annual Irrigation Main/Sys Replacements | 848000 | 2027-2040 | Local | Engineering
17 | I-022 1000 East - 1050 S to 1200 S | 37000 | 2027-2040 | Impact Fees, DP/Other | Engineering
18 | I-027 Heber City Public Wors Facility Exp Ph 2 | 86000 | 2027-2040 | Impact Fees | Engineering
19 | P-007 Mill Road Bike Lane - 1200 S to 2400 S* | 7000 | 2027-2040 | Local, Impact Fees | Engineering
20 | P-012 Daniels Road Bike Lane* | 1000 | 2027-2040 | Local, Impact Fees | Engineering
21 | P-016 Spring Sage Brush Canal Trail | 127000 | 2027-2040 | Impact Fees, DP/Other | Engineering
22 | P-017 100 West Trail - 500 N to 1000 S | 399000 | 2027-2040 | Local, Impact Fees | Engineering
23 | P-018 550 East Bike Lane* | 3000 | 2027-2040 | Local, Impact Fees | Engineering
24 | P-019 650 South Bike Lane - 1000 W to 1300 W * | 1000 | 2027-2040 | Local, Impact Fees | Engineering
25 | P-024 500 East Bike Lane - 500 N to 700 S | 0 | 2027-2040 | N/A | Engineering
26 | P-029 Red Ledges Public Trail | 1480000 | 2027-2040 | DP/Other | Engineering
27 | P-031 100 East Trail - 500 N to 600 S | 66000 | 2027-2040 | Local, Impact Fees | Engineering
28 | P-032 West Bypass Trail | 0 | 2027-2040 | N/A | Engineering
29 | P-033 County Park Connector Trail | 0 | 2027-2040 | N/A | Engineering
30 | P-038 Southfield Road Bike Lane | 7000 | 2027-2040 | Local, DP/Other | Engineering
31 | P-039 800 North Trail - Hwy 40 to 600 W | 0 | 2027-2040 | N/A | Engineering
32 | P-044 300 West Bike Lane - 100 S ot 500 N * | 0 | 2027-2040 | Local, DP/Other | Engineering
33 | P-047 800 North Neighborhood Park | 371000 | 2027-2040 | DP/Other | Engineering
34 | P-048 Red Ledges Community Park | 2471000 | 2027-2040 | DP/Other | Engineering
35 | P-051 Trailhead Facilities (various locations) | 62000 | 2027-2040 | Local, Impact Fees | Engineering
36 | P-053 1200 South Trail - 600 E to 1200 E * | 147000 | 2027-2040 | Local, DP/Other | Engineering
37 | P-056 Wasatch Canal Trail - Mill Rd to Center St | 0 | 2027-2040 | N/A | Engineering
38 | P-057 Wasatch Canal Trail - Center St to Vly Hills Dr | 0 | 2027-2040 | N/A | Engineering
39 | P-058 Wasatch Canal Trail - Vly Hills Dr to Coyote Ln | 0 | 2027-2040 | N/A | Engineering
40 | P-059 Hwy 189 Trail - 3000 S to South Bypass | 0 | 2027-2040 | N/A | Engineering
41 | P-061 600 West Trail - West Bypass to RR Sta | 0 | 2027-2040 | N/A | Engineering
42 | P-062 Rail Trail - RR Sta to City Boundary | 0 | 2027-2040 | N/A | Engineering
43 | P-063 Muirfield Park Trail - West Bypass to Park | 0 | 2027-2040 | N/A | Engineering
44 | P-066 300 East Bike Lane - Coyote Ln to 800 N | 7000 | 2027-2040 | Local, DP/Other | Engineering
45 | P-068 600 South Trail - 600 E to Mill Rd | 0 | 2027-2040 | N/A | Engineering
46 | P-069 500 East Bike Lane - 1200 S to Hwy 40 | 4000 | 2027-2040 | Impact Fees, DP/Other | Engineering
47 | P-071 West Fields Neighborhood Park | 494000 | 2027-2040 | DP/Other | Engineering
48 | P-072 Turner Mills Neighborhood Park | 247000 | 2027-2040 | DP/Other | Engineering
49 | P-077 Peterson Annexation Neighborhood Park | 371000 | 2027-2040 | DP/Other | Engineering
50 | P-078 Master Plan Updates every 5 years (4 times) | 48000 | 2027-2040 | Impact Fees | Engineering
51 | S-020 Aerial Digital Map Updates (4 times) | 15000 | 2027-2040 | Impact Fees | Engineering
52 | S-021 Master Plan Update (4 times) | 177000 | 2027-2040 | Impact Fees | Engineering
53 | S-025 Sage Br Spring Cr Canal - 300 N to 100 S (24") | 810000 | 2027-2040 | Impact Fees | Engineering
54 | S-026 Sr-113 - 800 W to 930 W | 549000 | 2027-2040 | Impact Fees | Engineering
55 | S-027 SR113- 930 W to Southfield Rd | 566000 | 2027-2040 | Impact Fees | Engineering
56 | S-030 Annual Sewer Main/Sys Replacements | 18200000 | 2027-2040 | Local | Engineering
57 | S-031 South Field Road - Hwy 40 to 1200 S (10") | 1141000 | 2027-2040 | DP/Other | Engineering
58 | S-032 Hwy 189 - 3000 S to South Field Rd (10") | 1183000 | 2027-2040 | DP/Other | Engineering
59 | S-033 Hwy 40 - Center Cr to E Airport (East) | 455000 | 2027-2040 | DP/Other | Engineering
60 | S-038 500 North to Midway Lane | 992000 | 2027-2040 | Local, DP/Other | Engineering
61 | S-039 South Field Road Lift Station | 260000 | 2027-2040 | DP/Other | Engineering
62 | S-040 East Airport Rd - 100 E to Daniel Rd (12") | 177000 | 2027-2040 | Impact Fees | Engineering
63 | S-041 Heber City Public Works Facility Exp Ph.2 | 825000 | 2027-2040 | Impact Fees | Engineering
64 | S-045 1200 South - 1000 E to 1200 E | 306000 | 2027-2040 | Local, DP/Other | Engineering
65 | T-003 400 South - 600 E to 700 East & Bridge * | 305000 | 2027-2040 | Impact Fees | Engineering
66 | T-008 700 N - 500 E to Main St | 908000 | 2027-2040 | DP/Other | Engineering
67 | T-009 600 East - 200 South to 400 South | 328000 | 2027-2040 | DP/Other | Engineering
68 | T-010 400 East - 500 North to 700 North | 365000 | 2027-2040 | DP/Other | Engineering
69 | T-012 300 West - 500 North to 100 South * | 0 | 2027-2040 | N/A | Engineering
70 | T-016 2400 South - Daniels to S. Airport Rd | 0 | 2027-2040 | N/A | Engineering
71 | T-018 Airport Road - Daniels Rd to Hangers | 711000 | 2027-2040 | Local, Impact Fees, DP/Other | Engineering
72 | T-028 500 East - 500 North to 600 South | 0 | 2027-2040 | N/A | Engineering
73 | T-031 Daniels Rd - 2300 S to 2500 S * | 365000 | 2027-2040 | Local, Impact Fees, DP/Other | Engineering
74 | T-032 Industrial Pkwy - 910 South to Hwy 189 | 847000 | 2027-2040 | Impact Fees, DP/Other | Engineering
75 | T-033 600 West - 700 N to 100 S | 0 | 2027-2040 | N/A | Engineering
76 | T-035 1200 South - 600 W to Southfield Rd | 949000 | 2027-2040 | Impact Fees, DP/Other | Engineering
77 | T-036 100 South - Main St. to Southfield UDOT | 0 | 2027-2040 | N/A | Engineering
78 | T-040 1200 East - 1200 S to Hwy 40 * | 1106000 | 2027-2040 | Impact Fees, DP/Other | Engineering
79 | T-042 Master plan Update (4 times) | 192000 | 2027-2040 | Impact Fees | Engineering
80 | T-043 100 East - 500 North to 600 South | 1132000 | 2027-2040 | Local, Impact Fees | Engineering
81 | T-044 West Bypass - 900 N to 1300 S | 0 | 2027-2040 | N/A | Engineering
82 | T-046 100 West - 500 North to 1000 South | 2420000 | 2027-2040 | Local, Impact Fees | Engineering
83 | T-047 S. Airport Rd - Hwy 189 to Airport Rd | 0 | 2027-2040 | N/A | Engineering
84 | T-048 Southfield Road - 1200 S to Hwy 189 | 0 | 2027-2040 | N/A | Engineering
85 | T-052 500 East - 600 S to 720 S | 183000 | 2027-2040 | Impact Fees, DP/Other | Engineering
86 | T-054 150 East - Coyote Lane to 700 N | 1646000 | 2027-2040 | Impact Fees, DP/Other | Engineering
87 | T-059 Downtown Angled Parking - 400 N to 500 S | 0 | 2027-2040 | N/A | Engineering
88 | T-060 Annual Rd Maint - Stripe, Seal, Overlay, Dips | 22659000 | 2027-2040 | Local | Engineering
89 | T-061 Annual Sidewalk New Construction & Repair | 3078000 | 2027-2040 | Local | Engineering
90 | T-065 500 North to Midway Lane | 2303000 | 2027-2040 | Impact Fees, DP/Other | Engineering
91 | T-068 Heber City Public Works Facility Exp Ph2 | 1512000 | 2027-2040 | Impact Fees | Engineering
92 | T-072 600 South - 300 W to 600 W * | 475000 | 2027-2040 | Local, Impact Fees | Engineering
93 | T-073 IHC Ring Road South - 1500 S 500 E | 694000 | 2027-2040 | Impact Fees, DP/Other | Engineering
94 | T-074 Center St Widening - 1400 E to the East | 0 | 2027-2040 | N/A | Engineering
95 | W-005 Daniels Road - 2200 S to 2500 S (8") | 237000 | 2027-2040 | DP/Other | Engineering
96 | W-019 2400 South - Daniels Rd to Airport Rd (12") | 769000 | 2027-2040 | Impact Fees, DP/Other | Engineering
97 | W-025 1250 South PRV | 134000 | 2027-2040 | Impact Fees | Engineering
98 | W-027 New Source Development (1600 gpm) | 2870000 | 2027-2040 | Impact Fees | Engineering
99 | W-028 Master Plan Updates every 5 years (4 times) | 177000 | 2027-2040 | Impact Fees | Engineering
100 | W-029 Aerial Digital Map Updates (4 times) | 15000 | 2027-2040 | Impact Fees | Engineering
101 | W-033 400 West - 400 N to 300 S (8") | 796000 | 2027-2040 | Local, Impact Fees | Engineering
102 | W-036 400 East - 800 N to Center St (8") | 658000 | 20207-2040 | Local, Impact Fees | Engineering
103 | W-037 200 East - 500 N to 600 S (8") | 1131000 | 2027-2040 | Local, Impact Fees | Engineering
104 | W-038 500 South - 300 W to Main St (8") * | 108000 | 2027-2040 | Local, Impact Fees | Engineering
105 | W-044 Highway 40 - 2400 S to 2700 S West (8") | 469000 | 2027-2040 | DP/Other | Engineering
106 | W-045 1200 South - 850 W to 1200 W (8") | 188000 | 2027-2040 | DP/Other | Engineering
107 | W-046 1200 West - 1200 S to 1100 S (8") | 182000 | 2027-2040 | DP/Other | Engineering
108 | W-047 600 West - 450 S to 650 S (8") * | 282000 | 2027-2040 | Impact Fees | Engineering
109 | W-051 200 West - 300 N to 200 S (8") | 537000 | 2027-2040 | Local, Impact Fees | Engineering
110 | W-053 550 North - 550 E to 750 E (8") | 226000 | 2027-2040 | Local, Impact Fees | Engineering
111 | W-054 Future Tank Storage (1.35 mg See I-001) | 3000000 | 2027-2040 | Impact Fees | Engineering
112 | W-056 Annual Water Main/Sys Replacements | 12530000 | 2027-2040 | Local | Engineering
113 | W-058 South Field Rd/SR189 - 1100 S to City Line | 1527000 | 2027-2040 | DP/Other | Engineering
114 | W-059 SR189 - City Line to 3000 S (12") | 365000 | 2027-2040 | DP/Other | Engineering
115 | W-060 500 North to Midway Lane (8") | 454000 | 2027-2040 | DP/Other | Engineering
116 | W-063 Hwy 40 - 1500 to 1200 E East (8") | 547000 | 2027-2040 | DP/Other | Engineering
117 | W-064 Valley Drive PRV | 2120000 | 2027-2040 | Local | Engineering
118 | W-065 2400 South - S Airport Rd to Hwy 40 | 889000 | 2027-2040 | Impact Fees | Engineering
119 | W-068 Heber City Public Works Facility Exp Ph 2 | 781000 | 2027-2040 | Impact Fees | Engineering
120 | W-069 2400 South PRV | 134000 | 2027-2040 | Impact Fees | Engineering
NEEDS AND PRIORITIES
| IDENTIFIED NEED | COST | SOURCE | PRIORITY | START
| Phase 1 of Downtown Water and Sewer Replacement | 24000000 | Local, CIB, CDBG | 1 | 2022
| Eastern Bypass Road | 2500000 | Local, CIB | 2 | 2022
| Traffice Improvement Study | 150000 | Local, CIB | 3 | 2022
| Land Purchase for Affordable Housing | 1000000 | Local, CDBG, CIB | 4 | 2022
| Central Heber Pressureazed Irrigation Project | 7753000 | Local, CIB | 5 | 2022
| Red Ledges Park | 2764000 | Local, CIB, Impact Fees | 6 | 2022
| Muirfield Park Expansion | 3642000 | Local, CIB, Impact Fees | 7 | 2022
| Cemetery Expansion Phase 1 | 2976000 | Local, CIB, Impact Fees | 8 | 2022
| Citywide Fiber Installagtion | 21000000 | Local, CIB, Bonds | 9 | 2022
| Wasatch Vista Park | 75000 | Local, CDBG, Impact Fees, CIB | 10 | 2022-2025
| Irrigation Meter Project | 2346000 | Local, CIB | 11 | 2025
| West Side of Main Street Sidewalk 400 South to 500 South | 95000 | Safe Sidewalk, Local Funds | 12 | 2025
| 910 S. Sidewalk from 100 West to 600 West (T061) | 80000 | CDBG, Local Funds | 13 | 2025
| Western Truck Route | 100000000 | Private, UDOT, City, County, CIB | 14 | 2022
| Downtown Improvements | 10000000 | UDOT, CIB, Local | 15 | 2022
| Coyote Park | 200000 | Local, CIB | 16 | 2025
| New City Hall | 5000000 | Local, CDBG, CIB, Bonds | 17
Applicant Priority | County Area Priority | Entity | Project Description | Estimated Total Cost | Revenue Sources/Shares | PCIFB Request | PCIFB Submission Date
|  | Heber City | Phase 1 of Downtown Water and Sewer Replacement | 24000000 | Local, CIB, CDBG | Gran, Loan | 2022
A | A
|  | Heber City | Eastern Bypass Road | 2500000 | Local, CIB | Grant. Loan | 2022
B | B
|  | Heber City | Traffic Improvement Study | 150000 | Local, CIB | Grant | 2022
C | C
|  | Heber City | Land for Affordable Housing | 1000000 | Local, CDBG, CIB | Grant | 2022
D | D
E | E | Heber City | Central Heber Pressurized Irrigation Project | 7753000 | Local, CIB | Grant, Loan | 2021-2040
F | F | Heber City | Red Ledges Park Fitness Court and Trails | 2764000 | Local, CIB, Impact Fees, Developer | Grant | 2022
G | G | Heber City | Muirfield Park Expansion and Amenities | 3642000 | Local, CIB, Impact Fees | Grant | 2022
H | H | Heber City | City Wide Fiber Installation | 21000000 | Local, CIB, Bonds | Grant, Loan | 2022
I | I | Heber City | Cemetery Phase 1 Expansion | 2976000 | Local, CIB, Impact Fees | Grant, Loan | 2022
J | J | Heber City | Irrigation Meter Project | 2346000 | Local, CIB | Grant, Loan | 2021-2025
K | K | Heber City | Coyote Park | 1775000 | Local, CIB, Impact Fees | Grant, Loan | 2022
L | L | Heber City | New City Hall | 5000000 | Local, CDBG, CIB, Bonds | Loan | 2025
M | M
N | N

## Independence
Independence
Wasatch County
Town of Independence
Applicant Priority | A
County Area Priority | A
Entity | Independence
Project Description: | Center Creek Road 7 miles
Est. Total Cost: $6,500,000
Revenue Sources/Shares: CIB
CIB Request | Grant
CIB Submission | 2021

## Coalville
SUMMARY OF 2022 CAPITAL IMPROVEMENT PROJECTS Jurisdiction: COALVILLE CITY
SHORT TERM (1 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | EST. START DATE | REVENUE | RESP. DEPT
SOURCES/AMOUNTS
1 | Culinary Water lines on 200 North and Center Street from approx. 60 West | $300,000 | 2022 | CDBG/City | Mayor/Council/Staff
Funds/Grant/CIB/
Possible Loans
2 | Storm Drain between 100 S. and 150 S. | $100,000 | 2022 | City Funds/CDBG/DDW | Mayor/Council/Staff
3 | Irrigation Pond Lining | $350,000 | 2022 | City Funds/ | Mayor/Council/Staff
CDBG/DDW/CIB/Grants and Possible Loans
4 | Other Storm Drain needs | $300,000 | 2022 | City Funds/CDBG/CIB | Mayor/Council/Staff
5 | Street Improvement | $250,000 | 2022 | City Funds | Mayor/Council/Staff
Projects
6 | South Lift Station/ | $1,325,790 | 2022 | ARPA/USDA/City Funds | Mayor/Council/Staff
Force Main
MEDIUM TERM (5 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | EST. START DATE | REVENUE | RESP. DEPT
SOURCES/AMOUNTS
1 | Storm Drains | $500,000 | 2022 | City Funds/ | Mayor/Council/Staff
CDBG/CIB/Grants and Possible Loans
2 | Side Walk Replacement | $500,000 | 2023 | City Fund/Safe Routes To School/CDBG | Mayor/Council/Staff
3 | Community Trail Project | $500,000 | 2024 | State Parks/UDOT | Mayor/Council/Staff
Enhancement/RAP
4 | Additional Phases of the Community Park/ Softball Complex | $1,000,000 | 2025 | RAP/City | Mayor/Council/Staff
Funds/LWCF/Other
Private Funds
Page 1 of 3
5 | Improve entrances into the City and other major travel corridors | $250,000 | 2026 | City Funds/CDBG/TA | Mayor/Council/Staff
LONG TERM (5-10 YEARS)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | EST. START DATE | REVENUE | RESP. DEPT
SOURCES/AMOUNTS
1 | Storm Drain Upgrades | $2.3 Million | 2031 | Storm Drain Fees | Public Works
2 | Beacon Hill Drive New Street Alignment | $1.2 Million | 2031 | Non-Urban UDOT/City B&C Funds | Public Works
3 | 250 East New Street | $1.5 Million | 2031 | Non-Urban UDOT/City B&C Road Funds | Public Works
4 | Multiple Street Widening Projects | $3.4 Million | 2031 | Looking For Funds/May need to bond on B&C Road Funds | Public Works
5 | Pedestriana Walkway over I-80 | $1.5 Million | 2031 | Non-Urban UDOT/City B&C Road Funds | Public Works
6 | Extend Pioneer Drive and Connect to Beacon Drive | $2.0 Million | 2031 | Looking For Funds/May need to bond on B&C Road Funds | Public Works
NEEDS AND PRIORITIES
PRIORITY | IDENTIFIED NEED | COST | START | SOURCE
1 | Irrigation Pond Lining | $350,000 | 2022 | City Funds/
CDBG/DDW/CIB/Grants and Possible Loans
2 | Culinary Water Lines | $300,000 | 2022 | CDBG/City
Funds/Grant/CIB/
Possible Loans
3 | Storm Drains | $500,000 | 2022 | City Funds/
CDBG/CIB/Grants and Possible Loans
4 | Street Improvement | $250,000 | 2022 | City Funds
Projects
Page 2 of 3
5 | Side Walk Replacement | $500,000 | 2023 | City Fund/Safe Routes To School/CDBG
6 | South Lift Station/ | $1,325,790 | 2022 | ARPA/USDA/City Funds
Force Main

## Kamas
SUMMARY OF CAPITAL IMPROVEMENT PROJECTS
Jurisdiction: | Kamas City
Date: | 2021-09-21
SHORT TERM (1 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | EST. START DATE | REVENUE SOURCES/ AMOUNTS
1 | Sewer Improvements | 150000 | 2022 | CDBG/Sewer
2 | Kamas Park Improvements | 142200 | 2021 | RAP Tax Grant/General Fund/Summit County
3 | City Hall Improvements Window Replacement | 6000 | 2021 | General Fund
4 | Beaver Creek Culvert Extension/Water Line Replacement | 215000 | 2020-2021 | Water/Class C Road Funds/Road Impact Fees, Summit Count TFIP
5 | Update Safe Routes to School | 20000 | 2022 | General Fund, UDOT
6 | Bleacher Replacement | 750000 | 2021 | General Fund
7 | Park Building (Building & Erection) | 900000 | 2021 | General Fund
8 | Park Building (Finish Interior, Parking Lot) | 1160500 | 2021-2022 | General Fund/RAP Tax
9
MEDIUM TERM (5 YEAR)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | ESTIMATED START DATE | REVENUE SOURCES/ AMOUNTS
1 | Road Repairs & Maintenance | 150000 | Yearly | General Fund/Class B
2 | Slip Lining | 250000 | 2022 | CDBG/Sewer
3 | Water Valves | 20000 | 2023 | CDBG/Water
4 | Emergency Management Plan | 10000 | 2022 | General Fund
5 | Grassy Creek Park | 75000 | 2022 | Park Impact Fees/General Fund
6 | Sewer System Upgrade | 5000000 | 2022 | Sewer Fund/Impact Fees/DEQ
7 | Main Street Beautification | 600000 | 2023 | CIB Loan/ Grants/ UDOT
8 | Center Street Beautification | 350000 | 2024 | CIB Loan/ Grants/ UDOT
9
LONG TERM (5-10 YEARS)
RANK | PROJECT DESCRIPTION | TOTAL EST. COST | ESTIMATED START DATE | REVENUE SOURCES/ AMOUNTS
1 | Park Development | 50000 | 2025 | CDBG/Impact Fees
2 | Center Street Bridge | 250000 | 2025 | Road Impact Fees/Class B Roads
3
4
5
NEEDS AND PRIORITIES
| IDENTIFIED NEED | COST | SOURCE | PRIORITY
| Complete Water System Upgrades as per Master Plan | $250,000/year | Impact Fees & CDBG Grants | High
| Complete Sewer System Upgrades as per Master Plan | $250,000/year | Impact Fees & CDBG Grants | High
| Road Resurfacing | $150,000/year | Class C Road Fund & General Fund | High
| Main Street Beautification | 600000 | CIB Loans/ Grants/ UDOT | Medium
| Main Street Beautification | 600000 | CIB Loans/ Grants/ UDOT | Medium
| Center Street Beautification | 350000 | CIB Loans/ Grants/ UDOT | Medium
| Study on Necessity of Storm Drain System | 60000 | General Fund | Low
| Purchase of Maintenance Vehicles | 120000 | General Fund | Low

## Wasatch County
WASATCH COUNTY
| Short | 1 | Senior Citizen Housing | 2000000 | 7/31/2022 | CDBG, HUD, FMHA, USDA Rural Dev., WCHA, MAG | County Manger
|  | 2 | Flood Control | 3000000 | 3/1/2021 | NRCS, County General Funds | County Councils
|  | 3 | Road Shop at Jordanelle | 3000000 | 4/1/2023 | General Fund, B&C Roads, Mineral Lease | County Manager
|  | 4 | Roads Equipment | 1000000 | 4/1/2022 | B&C Road Funds, Mineral Lease | Roads Department
|  | 5 | Equipment (Roads, Solid Waste, Senior Citizens, and Motor Pool) | 1400000 | 4/1/2021 | PCIB, General Fund, CDBG | County Council, County Manager
|  | 6 | Fire Station | 10000000 | 4/1/2021 | Impact Fees, Donations, ARPA grants, property taxes | Fire Board, Fire Chief
|  | 7 | Parks Amenities (Pickle Ball addition, Event Complex) | 1625000 | 4/1/2021 | P&R Impact Fees, RAP Tax, Property Taxes | Parks and Recreation Board
|  | 8 | Solid Waste Facilities Expansion | 2500000 | 7/1/2021 | PCIB, 54-Fund Budget | County Council
| Medium | 1 | Road and Buildings | 4000000 | 4/1/2022 | B&C Road Funds, CIB, General Fund | County Manager, Public Works
|  | 2 | Public Works Equipment | 2000000 | 1/1/2026 | B&C Road, CIB, General Fund | County Manager, Public Works
|  | 3 | Fire Station Medical Equipment and FFE | 1500000 | 5/1/2023 | Donations, ARPA grants, property taxes | Fire Board, Fire Chief
|  | 3 | Senior Citizens, Mental Health Housing & ADA Ramp at Admin Building | 2000000 | 6/1/2024 | CDBG, HUD, FMHA/Rural Dev., WCHA | County Manager, Public Works
|  | 4 | Courthouse Expansion | 4000000 | 10/1/2024 | General Funds, District Court Funding | County Councils, County Manager
|  | 5 | Expanded health/Behavioral Health Facility | 2000000 | 4/1/2024 | General Funds | County Council, County Manager
|  | 6 | Flood Control | 2500000 | 10/1/2022 | General Funds, Mitigation Grants | City and County Councils, County Manager
|  | 7 | Animal Services Facility | 1500000 | 4/1/2023 | General Funds, Impact Fees | County Council, County Manager, Sheriff's Office
|  | 8 | Parks Amenities (Pickle Ball, Event Complex, Playgrounds) | 1125000 | 10/1/2026 | Impact Fees, RAP Tax, Property Taxes | Parks and Recreation Board
| Long | 1 | Roads | 10000000 | 1/1/2027 | B&C Road, CIB, General Fund | County Manager, Public Works
|  | 2 | Public Safety/Road Shops at Strawberry | 2000000 | 1/1/2027 | Fire District, B&C Roads, Mineral lease | City and County Councils
|  | 3 | Public Works Equipment | 2000000 | 1/1/2026 | B&C Road, CIB, General Fund | County Manager, Public Works
|  | 4 | Expanded Sheriff's Office | 5000 | 1/1/2026 | General Fund, Impact Fees | County Manager, Sheriff's Office
|  | 5 | Administration Building | 15000000 | 1/1/2026 | Revenue Bond, CIB, Sales Tax, G.O.Bond | City and County Councils, County Manager
|  | 6 | Sheriff Covered Parking for equipment | 1000000 | 1/1/2026 | General Fund, Impact Fees | County Manager, Sheriff's Office
|  | 7 | Sheriff Equipment Shed | 500000 | 1/1/2026 | General Fund, Impact Fees | County Manager, Sheriff's Office
|  | 8 | Sheriff Jordanelle Station | 400000 | 1/1/2028 | General Fund, Impact Fees | County Manager, Sheriff's Office
|  | 9 | West-County Sheriff Station | 400000 | 1/1/2031 | General Fund, Impact Fees | County Manager, Sheriff's Office
|  | 10 | North Regional Park | 35000000 | 1/1/2031 | General Fund, Impact Fees, RAP Tax | Parks and Recreation Board

## Midway
MIDWAY FY2021 submission
| Short | 1 | 2021 Road Projects | 350000 | Summer 2021 | General Fund, Impact Fees | Engineering/Public Works
|  | 2 | 2021 Water Projects | 910000 | Summer 2021 | Water Fund, Impact Fees | Engineering/Public Works
|  | 3 | 2021 Road Surface Treatment | 250000 | Summer 2021 | General Fund | Engineering/Public Works
|  | 4 | 2021 Trail Surface Treatment | 45000 | Summer 2021 | General Trail Fund | Engineering/Public Works
|  | 5 | Park Improvements | 70000 | Summer 2021 | General Fund, Impact Fees | Public Works
|  | 6 | Building Improvements | 50000 | Summer 2021 | General Fund | Building Department
|  | 7 | Improved SKADA System | 75000 | Summer 2021-22 | Water Fund, Impact Fees
| Medium | 1 | Road Projects | 350000 | Yearly | General Fund, Impact Fees | Engineering
|  | 2 | Water Projects | 850000 | Yearly | Water Fund, Impact Fees | Engineering
|  | 3 | Road Surface Treatment | 200000 | Yearly | General Fund | Engineering
|  | 4 | Upgrade the Water GIS System | 100000 | 2022 | Water Fund | Engineering/Public Works
|  | 5 | Trail Surface Treatment | 45000 | Yearly | General Fund | Engineering
|  | 6 | Upgrade the Storm Drain GIS System | 75000 | 2022 | General Fund | Engineering/Public Works
|  | 7 | Park Improvements | $70,000/year | Yearly | General Fund, Impact Fees | Public Works
|  | 8 | Building Improvements | $50,000/year | Yearly | General Fund | Building Department
|  | 9 | Homestead Trail | 1000000 | 2022 | Trail Fund, Trail IF, Grants | Engineering
| Long | 1 | Road Projects | 350000 | Yearly | General Fund, Impact Fees | Engineering
|  | 2 | Water Projects | 850000 | Yearly | Water Fund, Impact Fees | Engineering
|  | 3 | Road Surface Treatment | 200000 | Yearly | General Fund | Engineering/Public Works
|  | 4 | Trail Surface Treatment | 45000 | Yearly | General Fund | Engineering
|  | 5 | Park Improvements | $70,000/year | Yearly | General Fund, Impact Fees | Public Works
|  | 6 | Building Improvements | $50,000/year | Yearly | General Fund | Building Department
| Needs/ Priorities | 1 | Improved Mapping & GIS System | 200000 | Unknown | General, Unknown | Engineering/Public Works
|  | 2 | Improved SKADA System | 75000 | Unknown | General, Unknown | Engineering/Public Works
|  | 3 | Upgrade Culinary Meter System | 300000 | Unknown | General, Unknown | Engineering/Public Works
|  | 4 | Improve the Midway Trial System | Unknown | Unknown | General, Unknown | Engineering/Public Works

## Self-Assessment
Jurisdiction Self Assessment 2021 (Using a scale of 1 to 10, 1 meaning completely inadequate to 10 meaning extremely well-addressed) x=No Response
| Fire Department Facilities | Fire Department Equipment | Fire Department Staffing/Volunteers | Police/Public Safety Facilities | Police/Public Safety Staffing | Recreational Facilities (including Parks) | Community Sewer System | Culinary Water Source | Culinary Water Storage | Culinary Water System Distrubtion | Streets and Roads | Streets and Road Maintenance | Solid Waste Disposal | Health Care | Animal Control | Courts | Jails | Senior Center (or access to Senior Center) | Services to Assist Homeless Individuals
Charleston
Coalville
Daniel
Francis | 8 | 8 | 8 | 8 | 8 | 7 | 10 | 8 | 6 | 8 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 2
Heber | 7 | 8 | 7 | 9 | 7 | 6 | 9 | 9 | 9 | 8 | 8 | 8 | 9 | 8 | 9 | 9 | 8 | 8 | 3
Henefer | 8 | 8 | 8 | 8 | 8 | 5 | 6 | 4 | 4 | 4 | 7 | 2 | 8 | N/A | 8 | N/A | N/A | N/A | N/A
Hideout
Kamas | 9 | 8 | 9 | 9 | 8 | 7 | 7 | 9 | 9 | 8 | 6 | 6 | 8 | 8 | 4 | 8 | 9 | 9 | 3
Midway (FY2015) | 9 | 9 | 8 | 8 | 8 | 7 | 9 | 8 | 9 | 9 | 8 | 7 | 9 | 8 | 8 | 8 | 8 | 7 | 3
Oakley (FY2017)
Park City
Summit County
Wallsburg (2014)
Wasatch County | 5 | 6 | 7 | 7 | 6 | 6 | 7 | 6 | 6 | 6 | 6 | 6 | 5 | 6 | 3 | 4 | 5 | 7 | 4

## Interlaken
Interlaken
Roads, Fire Control, Water & Trash | 1500000 | 2022-03-01